Additional summarizing report to the

Interim report for the first year, October 15, 2006 – October 14, 2007

Summary of the work done during the first year

Products

| P | Project webpage | EVLM Portals | Info leaflet | CD EVLM structure | List of Database materials1 | Teacher´s guide chapters CDs |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Central | Central | English | missing | OK | X |
| 2 | Bulgarian | BG | Bulgarian 2x | X | OK | OK |
| 3 | Czech | CZ done | Czech done | missing | Missing done | done |
| 4 | Spanish | ES | Spanish | X | OK | OK |
| 5 | Finnish | FI done | Finnish done | X | Missing done | missing |
| 6 | Hungarian | HU | Hungarian | X | Missing done | missing |
| 7 | Irish | IE | Irish | X | OK | done |
| 8 | Slovak | SK | Slovak | missing | OK | OK |
| 9 | Central | X | English | missing |  | missing |

Missing products were finalised according to the new deadline – March 20, 2008, as had been agreed at the Meeting 5 of partners organised in Limerick, Ireland,  February 14 – 15, 2008.

Czech and Finnish portals are linked to the EVLM Central portal

http://www.evlm.stuba.sk/

Czech and Finnish leaflets are linked to the EVLM Project office on-line

http://www.evlm.stuba.sk/parea/aframe.htm

in menu item PRODUCTS - Leaflets

webMathematica portal (reponsible Partner 3, Czech republic) is working at the new address

http://89.102.237.170/web/EVLM/

Partner P3 circulated the sample file for DBSearch upload to all partners, who started to populate the Database Search with materials they supported to the EVLM Central database.

List of materials in national EVLM databases of partners P3 (Czech republic), P5 (Finnland) and P6 (Hungary) were delivered and are attached.

Improvements to the project national webpages indicated in the table below were done by all concerned partners.

| P | Links to other Ps pages | Correct addresses | Partners | Links to portals Central National |
| --- | --- | --- | --- | --- |
| Central | correct all | http://evlm.stuba.sk/EVLM/index.html | correct | correct |
| BG | correct all | http://www.fmi-plovdiv.org/evlm/EVLMbg/EVLMbg.htm | correct | correct both |
| CZ | Central, BG, ES, FI, SK done | http://home.zcu.cz/~benedikt/EVLM/ | Tulossilata / Tulossilta | done |
| ES | correct | http://evlmspain.usal.es/ | Tulossilata / Tulossilta | correct both |
| FI | Central, BG, CZ, ES, IE, SK, UK done | http://www.tulossilta.fi/EVLM/ | Tulossilata / Tulossilta | done |
| HU | done | http://www.uni-miskolc.hu/~evlmhu/ | Tulossilata / Tulossilta | correct both |
| IE | done | http://www.ul.ie/evlm/ | done | correct both |
| SK | correct all | http://evlm.stuba.sk/EVLM/slovak/ | correct | correct both |
| UK | correct all | http://www.coventry.ac.uk/ec/evlm/ | done | done |

Missing reports for the reporting periods of the first year were delivered to coordinator and are attached as follows:

Partner 3 – Deliverable frontpage for Czech portal, Deliverable frontpage for Czech leaflet, Deliverable frontpage for Czech Math centre, sample of Czech leaflet.

Partner 5 – Interim reports 1 -3, Timesheets, Deliverable frontpage for Finnish project page, Deliverable frontpage for Finnish portal, Deliverable frontpage for Finnish leaflet, Deliverable frontpage for Finnish Math centre.

Some of the EVLM portals improvements indicated in the table below were done by respective partners, some are under the development

| P | Links to Central Portal | Correct addresses | Links to Nation. Portals | Stat. | Feedback | Consul online |
| --- | --- | --- | --- | --- | --- | --- |
| Centr. | x | http://evlm.stuba.sk | correct | OK | OK | OK |
| BG | correct | http://www.fmi-plovdiv.org/evlm/ | correct | OK | work on | work on |
| CZ | done | http://home.zcu.cz/~benedikt/EVLMPortal | no links | work on | work on | work on |
| ES | correct | http://evlmspain.usal.es/ | correct | OK | work on | work on |
| FI | done | http://www.tulossilta.fi/EVLMPORTAL/ | no links | done | done | work on |
| HU | correct | http://www.uni-miskolc.hu/evml/ | correct | done | done | done |
| IE | correct | http://www.ul.ie/evlm/ | no links | done | work on | work on |
| SK | correct | http://slovak.evlm.stuba.sk/portal/ | no links | OK | OK | OK |

Rests from the second year

Information booklets – English + national versions, printed copies

(due delivery was January 2008, month 16 - rest)

February 22 – draft from partner P7

February 29 – comments by partners

March 15 – final version (national versions) + upload to EVLM server, all partners

http://www.evlm.stuba.sk/parea/aframe.htm, item PRODUCTS, Booklets

March 30 – printed copies, all partners will provide samples of printed booklet

EVLM structure on CD (due delivery was July 2007, month 10 - rest)

March 20 - partial structure for checking and comments

http://www.evlm.stuba.sk/parea/aframe.htm, item PRODUCTS, DBManual

March 25 – comments form partners and English corrections by evaluator P9

April 3 – CD production, partners P3 + P8 (50 pcs. each)

Teacher’s guide book – English chapters+national translations, CD production

(due delivery was December 2007, month 15 - rest)

March 3 – 2 chapters by each partner (approx. 6-8 pages each) delivered

March 20 – English corrections + upload to EVLM server

http://www.evlm.stuba.sk/databasemenu/teacherbook/teacherbook.htm

April 30 - CD production, partners P2–P9 (60 pcs. each) (actual delivery month 19)

In Bratislava, March 31, 2008

doc. RNDr. Daniela Velichová, CSc.

Project coordinator

Strojnícka fakulta STU v Bratislave