# MINUTES from the 5th meeting of partners

Venue: University of Limerick, Ireland

Date:  February 14 - 15, 2008

### Present

Velichová Daniela, Slovak University of Technology in Bratislava, SK

Snezhana Georgieva Gocheva-Ilieva, Plovdivski University of Plovdiv, BG

Péter Körtesi, University of Miskolc, HU

Olivia Gill, University of Limerick, IE

Patrick Johnson, University of Limerick, IE

John Goodband, Coventry University, UK

Duncan Lawson, Coventry University, UK

Jiří Benedikt, West Bohemian University, Plzeň, CZ

Päivi Siltanen, Tilossilta Ltd., Tampere, FI

Dagmer Szarková, Slovak Society for Geometry and Graphics, SK

Absent with excuse

Daniela Richtáriková, Slovak Society for Geometry and Graphics, Bratislava, SK

Gerardo Rodriguez, University of Salamanca, ES

First Report/Money

First report was submitted to National Agency December 12th. National agency had 45 days for evaluation. No report to date. Daniela will ask again February 26th re: receipt of more money.

Partners need to have completed tasks to receive next instalment.

Webpages

Corrections to webpages to be finalised and to be uploaded to designated places on EVLM server.

CD of EVLM Structure

All webpages and portals necessary to complete CD.

Links to national portals and central portal must be present.

CD must contain a list of topics and materials – self standing CD – no links.

Portals

Duncan suggested removal of various topic headings to remove gaps in portal.

Finnish portal and Czech portal to be completed in one month (March 20th).

The material that each partner is responsible for must be in central database by March 20th.

Work Outstanding

Leaflets:

Czech and Finnish leaflets outstanding….to be completed by March 20th.

Reports:

Timesheets, reports and receipts due from Finnish partner.

Hungarian and Irish Portal:

Statistics link to be made live.

Feedback

Partners have been contracted to do 2 sets of feedback.

Two sets of feedback are to be collected from teachers and students. The first will be on the portal and the website and is to be delivered to Duncan by April 30th. The second is on the teachers’ guidebook and is to be delivered to Duncan by June 30th.

Partners must collect feedback using the same questionnaire.

Important Dates

| Deadline | Product | Responsibility |
| --- | --- | --- |
| February 22, 2008 | Information booklet draft | P7 |
| February 29, 2008 | Comments on booklet | all |
| March 3, 2008 | Search Files for central database sent to Jiří | all |
| March 3, 2008 | 2 chapters for Teacher’s book | P2-P9 |
| March 15, 2008 | Booklet final + national versions + upload to EVLM server | all |
| March 20, 2008 | All rests form the first year – products + reports English corrections of chapters in Teacher’s book EVLM structure CD upload - partial | all P9, upload P2-P8 P1+P8 |
| March 25, 2008 | Comments on EVLM structure CD | all |
| March 30, 2008 | Printed booklets – 250 pcs. each partner | P2 –P9 |
| April 3, 2008 | Teacher’s book CD production + 50 pcs. each | P3+P8 |
| April 15, 2008 | Interim report 4 + financial report 2 + TMS | all |
| April 30, 2008 | Teacher’s book CD production – 60 pcs. each Feedback 1 (from EVLM portals) Chapter 1 for Student’s book | P2-P9 P1-P8 all |
| May 15, 2008 | Feedback analysis 1 Chapter 2 for Student’s book + corrected chapter 1 | P9 all |
| May 30, 2008 | Chapter 3 for Student’s book + corrected chapter 2 | all |
| June 15, 2008 | Final English Student’s book+ national versions | all |
| June 30, 2008 | Feedback 2 (from teachers) | P1-P8 |
| July 4, 2008 | Student’s book CD production - 200 pcs. each | all |
| September 15, 2008 | Updated list of materials in databases Feedback analysis 2 | all P9 |
| October 1, 2008 | Interim report 5 | all |
| October 14, 2008 | Financial report 3 + TMS + last details Interim evaluation report | all P9 |
| December 12, 2008 | Final report | P1 + P9 |

Database

Input materials to search database.

Fill in xml file for every file uploaded to central database.

Subjects and topics must match subjects/topics list from central database list.

Full URL to files needed.

Name of WebMath search to be changed to “Database Search”

Send Xml files to Jiri by March 3rd.

Workplans for Year 2

Each partner outlined activities re: work and dissemination for year 2 of project.

Files for Server

Interim reports: 2 signed copies and 2 photocopies to be sent to Daniela

Timesheets: 2 original signed copies to be sent to Daniela

Expenses: Copies only to be sent to Daniela. Originals to be kept in partners’ own institutions.

Discussion of Chapters for Teachers’ Guidebook

Send 2 chapters to all partners and upload to server.

Must produce 60 CD’s by April 30th.

Add folder in server area called ‘Teachers’ Guidebook’ and put chapters into it.

Proposed structure of chapters for Teachers’ Guidebook:

Chapter 1 – Introduction - UK

Chapter 2 – Hungary - general

Chapter 3 – Finland - general

Chapter 4- Finland – general

Chapter 5 – Ireland - Geogebra

Chapter 6 – Ireland - Geogebra

Chapter 7 – Bulgaria - Derive

Chapter 8 – Slovak Republic - webMathematics

Chapter 9 – Hungary - Maple

Chapter 10 – Spain – Methematica

Chapter 11 – Spain - Matlab

Chapter 12 – Czech Republic - CalcCenter

Chapter 13 – Czech Republic - CalcCenter

Information Booklet

To contain information on central portal and database.

To be translated into all languages for dissemination at conferences.

Olivia/Paddy to create English version by February 22nd.

Responses/comments/feedback from partners by February 29th.

Final national versions to be printed by March 30th.

Deliverable frontpages on booklet to be delivered to Daniela

Virtual EVLM Meeting

To be arranged by Daniela for end of April

6th /7th Meetings of Partners

6th meeting to be held in Miskolc, Hungary June 23/24, 2008

7th meeting to be held in Tampere in September, 2008. The 1st and 2nd of September have been proposed as dates for the meeting….not finalised yet.

Dissemination

SEFI,  Loughborough, April 2008 – Poster presentation on EVLM (Duncan, Daniela)

Annual Maths teaching and learning conference, Coventry, September, 2008 (Duncan)

ALM 15, Philadelphia, July, 2008 (Olivia)

ICME, Mexico, July 2008 (Olivia)

Teaching and Learning Maths in Higher Education – Quarterly magazine (Duncan to write article)

Students’ Guidebook

25 chapters to be completed – 3 chapters for each partner

MAX length 6-8 pages for each chapter

Ireland – Maple

UK – 		Matlab

Slovak Rep – 	Publicon

Finland – 	Studying maths, Excellence for maths homework, how to avoid and solve problems in maths studies

Hungary - 	More applications of Maple

Bulgaria - 	System Mathematica

Czech Rep - 	Calc Centre

Spain – to be decided

in Limerick, February **, 2008

Olivia Gill

Daniela Velichová

coordinator

PROGRAMME

Thursday, February 14, 2008

10.00 Opening - presentation of the coordinator – information about work progress

Management - financial and other organisational issues

Work plan for the second year – details and agreements about reporting, deadlines

10.30 Roundtable discussion – partners’ reporting about work done so far, planned activities for the second year, dissemination plan

11.00 Information about Central Database search

Functionality, instruction on how to input information about new materials

Presentation by Partner 3, CR

12.00 Lunch

14.00 – 16.00 Teacher’s book finalization, discussion about chapters

16.00 Coffee break

16.30 Development of the dissemination booklet - suggestions and ideas

Final decisions about layout, contents and production

19.00 Dinner

Friday, February 15, 2008

10.00 – 12.00 Preparation of Student’s guide book

Contents – contributions from partners

Technical issues, organisation of the work, editing

Decisions and distribution of agreed chapters among partners, deadlines

12.00 Lunch

14.00 Overall discussion about cooperation in the partnership

Improvements, summary and final agreements on approaching deadlines

16.00 Closing